## Slide 1: Tech Titans
Team Members : Venkatesh Koya
Akanksha Mamidiga
Saikumar Manga
Venkatesh Mudam
Sushmitha Vadhireddy

## Slide 2
ACHIEVING SUCCESS THROUGH A BALANCED SCORECARD
Introduction:
Emphasize the importance of leadership in law enforcement.
Mention the need to quantify results alongside leading people.
What is a Balanced Scorecard (BSC)?
Introduced by Harvard Business School in 1992.
Used across various industries to measure organizational objectives.
Steps to Implement a BSC:
1.Define Organizational Objectives
Involve key individuals for input.
Build consensus on methods and measurements.
2.Measure Progress Across Stages
Beginning Stage: Initial metrics (previous state).
Present Stage: Current results (current state).
End Stage: Targeted objectives (future state).
Benefits of a BSC
Provides rich data from frontline efforts.
Creates cohesion, synergy, and ownership among employees.
Manga Saikumar

## Slide 3: SUMMARY OF THE 2002 OLYMPIC WINTER AND PARALYMPIC GAMES PROJECT MANAGEMENT
Project Overview:
  Held in Salt Lake City, Utah, USA.
  Five years in planning, $1.9 billion budget. and included 78 Olympic and 15 Paralympic events.
  Coordinated with federal and state agencies for infrastructure improvements.
Project Management Adoption:
  Initially perceived as relevant only to large construction and technical projects.
  Became a cornerstone, turning a $400 million deficit into a $100 million surplus.
Planning and Scheduling:
  Employed a Primavera software-based system with a cascading color-coded Work Breakdown Structure (WBS).
  Integrated planning across 57 functions and 22 venues.
  Used a Venue Integrated Planning Schedule (VIPS) to coordinate resources, budgets, and operational plans.
Execution and Monitoring:
  Schedulers ensured the project stayed on target despite not having discrete sequential tasks.
  Executive Roadmap kept top 100 activities visible and accountable. Also, External partners were regularly updated
Cost Management:
  Addressed a $400 million budget shortfall by distinguishing "must-have" from "nice-to-have" items.
  Budgets over $2,000 were tracked monthly through contract management/procurement systems.
Success and Outcome:
  The project was deemed a success by the International Olympic Committee.
  Integrated project management approach ensured a smooth operation and timely execution of the Games.
Venkatesh Mudam

## Slide 4: Effective Risk Management and Contingency Planning for the Salt Lake City Olympic Games
Proactive Risk Management:
The team addressed potential risks with contingency plans, new procedures, and mitigation techniques.
Security Enhancements Post-9/11:
Major redesigns for parking, vehicle screening, and protected transportation routes.
Federal assistance to cover increased security costs.
Effective Communication:
Developed a System for Tracking and Reporting (STAR) for centralized communication.
Daily updates and bulletins ensured seamless information flow.
Volunteer Engagement:
Recruited over 68,000 applicants.
Incentives and thorough training led to only 0.8% volunteer attrition.
Customer and Scenario Planning:
Engaged critical stakeholders in detailed tabletop exercises.
Simulations and quality circles identified and resolved issues efficiently.
Legacy and Efficiency:
The Games provided lasting infrastructure and financial support for future training venues.
Completed vendor payments within nine months, setting a new standard for efficiency.
Sushmitha Vadhireddy

## Slide 5: Crosstown Traffic in Kuala Lumpur – GD 04
Traffic Headaches Solution:
  Introduction of a cutting-edge IT-based system to alleviate congestion.
Economic Boom:
  Over the past 20 years, Kuala Lumpur has evolved into a bustling metropolis due to an IT-led economy.
Chronic Congestion:
  Rush-hour congestion is a significant issue in the Klang Valley and Multimedia Super Corridor regions.
Integrated Transport Information System (ITIS):
  A MYR400 million (USD 105 million) investment.
  Comprised of Advanced Traffic Management System (ATMS) and Advanced Traveller Information System (ATIS).
System Features:
  Coverage of 200 km of roadway.
  255 CCTV cameras, 728 automatic incident detection cameras, and 140 variable-message signs.
  Provides real-time traffic information and road warnings.
Project Benefits:
  Improved road usage and safety.
  Reduced traffic delays and accidents.
  Enhanced emergency response times and pollution reduction.
  Aids in future road planning.
Project Management:
  Managed by ITS Konsortium with a team of 30 professionals.
  Four key phases: Planning, Design and Prototyping (PDP), Acceptance, Testing and Procurement (ATP), Physical Implementation (PI), and Testing and Commissioning.
  Flexibility in implementation to adapt to external challenges
Venkatesh Koya

## Slide 6: Project Overview and Progress
Project Management and Development
Split Development Process:
  Core development rolled out early..
Communication and Problem-Solving:
  Team based in a single project office.
Timeline
ATP Completion:
  Most subsystems completed.
PI Phase:
  Started in Q3 2003.
Stage Testing and Commissioning:
  Begins around early 2005.
  Project wrap-up expected mid-2005.
System Features
Information Accessibility:
  Services include:
    Route Planner: Traffic volumes, accidents, nearby service stations.
    Driving Tips: Road safety and driver resources.
    Public Transport: Fares, routes, timetables.
Advanced Telecommunications:
  Potential to send information directly to drivers’ mobile phones. Akanksha Mamidiga

## Slide 7
THANK YOU